## Test Cases
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Python Code Paste Submission | 1. Open app 2. Select 'Paste Code' 3. Paste valid Python code 4. Click 'Run AI Analysis' | Valid Python code submitted via paste input | Language detected as Python; analysis results displayed with findings | Pass | Verify code paste input works end-to-end for Python | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
2 | Java Code Paste Submission | 1. Open app 2. Select 'Paste Code' 3. Paste valid Java class code 4. Click 'Run AI Analysis' | Valid Java code submitted via paste input | Language detected as Java; analysis results displayed with findings | Pass | Verify code paste input works end-to-end for Java | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
3 | Python File Upload | 1. Open app 2. Select 'Upload File' 3. Upload a .py file 4. Click 'Run AI Analysis' | Valid .py file uploaded via file uploader | File contents shown in preview; language detected as Python; analysis runs | Pass | Verify .py file upload and content preview | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
4 | Java File Upload | 1. Open app 2. Select 'Upload File' 3. Upload a .java file 4. Click 'Run AI Analysis' | Valid .java file uploaded via file uploader | File contents shown in preview; language detected as Java; analysis runs | Pass | Verify .java file upload and content preview | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
5 | Empty Code Submission | 1. Open app 2. Leave text area empty 3. Click 'Run AI Analysis' | No code provided by user | Warning message displayed: 'Please provide some code to validate' | Pass | Verify graceful handling of empty submission | Sprint 1 | Developer | — | — | — | Closed | Edge case
6 | Python Syntax Validation — Valid | 1. Paste syntactically correct Python code 2. Click 'Run AI Analysis' | Valid Python syntax submitted | Syntax check passes silently; analysis proceeds to AI agents | Pass | Verify valid Python syntax passes the validator | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
7 | Python Syntax Validation — Invalid | 1. Paste Python code with missing colon after if-statement 2. Click 'Run AI Analysis' | Syntactically invalid Python code | Error shown: 'Syntax Error Detected'; analysis agents are skipped | Pass | Verify syntax errors are caught before LLM analysis | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
8 | Java Syntax Validation — Valid | 1. Paste valid Java class with main method 2. Click 'Run AI Analysis' | Valid Java CompilationUnit submitted | Syntax check passes; analysis proceeds to AI agents | Pass | Verify valid Java syntax passes the javalang validator | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
9 | Java Syntax Validation — Invalid | 1. Paste Java code with missing semicolon 2. Click 'Run AI Analysis' | Syntactically invalid Java code | Error shown: 'Syntax Error Detected'; analysis skipped | Pass | Verify javalang catches Java syntax errors | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
10 | Language Auto-Detection — Python | 1. Paste Python code containing 'def' and ':' 2. Click 'Run AI Analysis' | Python heuristic keywords present in code | Language correctly identified as Python without LLM call | Pass | Verify fast heuristic detection for Python | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
11 | Language Auto-Detection — Java | 1. Paste Java code containing 'public class' 2. Click 'Run AI Analysis' | Java heuristic keywords present in code | Language correctly identified as Java without LLM call | Pass | Verify fast heuristic detection for Java | Sprint 1 | Developer | — | — | — | Closed | Milestone 1
12 | Code Analysis — SQL Injection (Python) | 1. Paste Python code with string-concatenated SQL query 2. Click 'Run AI Analysis' | SQL Injection vulnerability present in Python code | High severity 'SQL Injection' finding reported with line number |  | Verify Code Analysis Agent detects SQL injection in Python | Sprint 2 | Developer | — | — | — | Open | Milestone 2
13 | Code Analysis — SQL Injection (Java) | 1. Paste Java code with Statement + string concat SQL 2. Click 'Run AI Analysis' | SQL Injection vulnerability present in Java code | High severity 'SQL Injection' finding reported with line number |  | Verify Security Agent detects SQL injection in Java | Sprint 2 | Developer | — | — | — | Open | Milestone 2
14 | Security Agent — Hardcoded Secrets | 1. Paste Java code with hardcoded DB password string 2. Click 'Run AI Analysis' | Hardcoded credential string present in code | High severity 'Hardcoded Secrets' finding reported |  | Verify Security Agent detects hardcoded passwords | Sprint 2 | Developer | — | — | — | Open | Milestone 2
15 | Security Agent — XSS Detection | 1. Paste Java Servlet with unsanitized request parameter in HTML output 2. Click 'Run AI Analysis' | XSS vulnerability via reflected user input | High severity 'Cross-Site Scripting (XSS)' finding reported |  | Verify Security Agent detects XSS in Java servlets | Sprint 2 | Developer | — | — | — | Open | Milestone 2
16 | Security Agent — Weak Cryptography | 1. Paste Java code using MD5 MessageDigest 2. Click 'Run AI Analysis' | MD5 (weak hash algorithm) used for password hashing | High severity 'Weak Cryptography' finding reported; SHA-256 recommended |  | Verify Security Agent flags deprecated MD5 hashing | Sprint 2 | Developer | — | — | — | Open | Milestone 2
17 | Code Analysis — Code Smells (Triple Nested Loop) | 1. Paste Java code with 3 nested for-loops 2. Click 'Run AI Analysis' | O(n³) complexity triple-nested loop present | High/Medium severity 'Complexity Issue' finding reported |  | Verify Code Analysis Agent detects excessive loop nesting | Sprint 2 | Developer | — | — | — | Open | Milestone 2
18 | Multi-Agent Parallel Execution | 1. Submit code 2. Observe terminal logs during analysis | Both Code Analysis and Security agents must run concurrently | Terminal shows both '--- Running Code Analysis ---' and '--- Running Security Analysis ---' messages |  | Verify LangGraph fan-out runs both agents in parallel | Sprint 2 | Developer | — | — | — | Open | Milestone 2
19 | Severity Sorting of Results | 1. Submit code with mix of High, Medium, Low findings 2. Observe results order | Multiple findings of different severities returned | Results displayed in order: High (🔴) → Medium (🟡) → Low (🔵) |  | Verify findings are sorted by severity in the UI | Sprint 2 | Developer | — | — | — | Open | Milestone 2
20 | Clean Code — Zero Issues | 1. Paste simple, well-documented, clean Python/Java code 2. Click 'Run AI Analysis' | No significant code quality or security issues present | Success message: 'No code smells or vulnerabilities found! Fantastic job!' with balloon animation |  | Verify agent correctly identifies clean code with no false positives | Sprint 2 | Developer | — | — | — | Open | Milestone 2

## Bug Defect Log
Sl: No: | Bug ID | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | BUG-001 | syntax_validator.py was built but not wired into the agent pipeline — validation was never called | Sprint 1 | Developer | Functional Defect | Added 'validate_syntax' as a LangGraph node between detect_language and analysis agents | 24-Jul-2026 | Closed | Milestone 1 requirement missed in initial build
2 | BUG-002 | LangGraph conditional edge fan-out using lambda returning list caused incorrect routing | Sprint 2 | Developer | Integration Defect | Replaced lambda with proper route_after_syntax() function; used explicit edge list | 24-Jul-2026 | Closed | LangGraph API misuse corrected
3 | BUG-003 | Model 'gemini-1.5-flash-latest' returns 404 NOT_FOUND — deprecated model suffix | Sprint 2 | Developer | Environment Defect | Removed deprecated '-latest' suffix; changed to 'gemini-1.5-flash' | 24-Jul-2026 | Closed | Google deprecated all '-latest' model aliases
4 | BUG-004 | Embedding model 'text-embedding-004' returns 404 NOT_FOUND on API v1beta endpoint | Sprint 2 | Developer | Environment Defect | Replaced Google embeddings with local FastEmbed (BAAI/bge-small-en-v1.5) — no API quota | 24-Jul-2026 | Closed | Google v1beta API does not expose this embedding model
5 | BUG-005 | pip install sentence-transformers fails with [WinError 206] filename too long due to PyTorch deep paths | Sprint 2 | Developer | Environment Defect | Replaced sentence-transformers with fastembed which uses short ONNX paths; uninstalled torch | 24-Jul-2026 | Closed | Windows 260-character MAX_PATH limit exceeded
6 | BUG-006 | Model 'gemini-2.0-flash' returns RESOURCE_EXHAUSTED (429) — free tier quota exceeded | Sprint 2 | Developer | Environment Defect | Switched entirely to Groq API (llama-3.3-70b-versatile); 14,400 req/day free tier | 24-Jul-2026 | Closed | gemini-2.0-flash has near-zero free tier RPM
7 | BUG-007 | 'gemini-1.5-flash' returns 404 NOT_FOUND — langchain-google-genai uses v1beta which doesn't support this model | Sprint 2 | Developer | Environment Defect | Fully migrated all LLM calls to Groq (langchain-groq); removed langchain-google-genai dependency | 24-Jul-2026 | Closed | Old langchain-google-genai package version incompatible with current models

## Sprint Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a developer, I want to paste Python or Java code directly into the portal so I can get an automated review without uploading a file. | Must Have | None | Developer | Completed
Sprint 1 | Sprint 1 | US-002 | As a developer, I want to upload a .py or .java source file so I can review code from my real project files. | Must Have | US-001 | Developer | Completed
Sprint 1 | Sprint 1 | US-003 | As a developer, I want the system to automatically detect whether my code is Python or Java so I don't have to select the language manually. | Must Have | US-001 | Developer | Completed
Sprint 1 | Sprint 1 | US-004 | As a developer, I want the system to validate my code's syntax before running AI analysis so I receive meaningful feedback on broken code and avoid wasting API credits. | Must Have | US-003 | Developer | Completed
Sprint 1 | Sprint 1 | US-005 | As a developer, I want OWASP guidelines and secure coding standards to be indexed into a RAG pipeline so the security agent has authoritative, up-to-date context when scanning my code. | Must Have | None | Developer | Completed
Sprint 2 | Sprint 2 | US-006 | As a developer, I want a Code Analysis Agent to identify code smells, complexity issues, and design anti-patterns with severity scoring so I can improve code quality systematically. | Must Have | US-003 | Developer | Completed
Sprint 2 | Sprint 2 | US-007 | As a developer, I want a Security Vulnerability Agent to scan my code for OWASP-standard vulnerabilities (SQL Injection, XSS, Hardcoded Secrets, etc.) and classify them by type and severity with location-specific flagging. | Must Have | US-005 | Developer | Completed
Sprint 2 | Sprint 2 | US-008 | As a developer, I want the Code Analysis and Security Vulnerability agents to run in parallel via a LangGraph orchestrator so that overall analysis time is minimised. | Must Have | US-006, US-007 | Developer | Completed
Sprint 2 | Sprint 2 | US-009 | As a developer, I want all agent findings merged into a unified list sorted by severity (High → Medium → Low) so I can prioritise the most critical issues first. | Must Have | US-008 | Developer | Completed
Sprint 2 | Sprint 2 | US-010 | As a developer, I want the system's detection accuracy validated against sample Python and Java codebases containing known quality issues and vulnerabilities, so I can confirm the agents are working correctly. | Must Have | US-006, US-007 | Developer | Completed